## Risk Assessment And Control_1
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11 |  |  |  |  | Trivial | 1-2 | Departmental Use only |  | COMPLETED
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 04.04.2022 |  |  |  |  | Acceptable | 3-4 | Revision No. | 1 | IN PROGRESS
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 2 |  |  |  |  | Moderate | 5-9 | Revision Date | 15.07.2022 | PENDING
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Production
[8 empty] | Intolerable | 20-25 | Unit | PID1
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity: Ceramic burner replacement in HBS |  | RISK LEVEL WITH EXISTING CONTROL | [6 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
1.Fall of bricks, steel, hammer, rope, wooden plank etc on human body as well as on Ceramic Burner from top of Combustion Chamber. | Company employees Contractor employees Supervisors | Blanking of combustion chamber with wooden planks Restriction of entry into stove dome by closing manhole Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 1 | 1 | [5 empty] | 0
2. Fall of broken parts of refractory from Hot blast main opening | Company employees Contractor employees Supervisors | Thorough Inspection of the site before starting activity Skilled Workmen Safety Awareness/traning Use of PPE. | 2 | 1 | 2
3. Fall of Combustion Chamber wall | Company employees Contractor employees Supervisors | Expert opinion Visual inspection of combustion chamber wall for the condition Incase of any doubt activity will be discontinued | 2 | 2 | 4
4. Collapsing of stove dome | Company employees Contractor employees Supervisors | Expert opinion Visual inspection of combustion chamber wall for the condition Incase of any doubt activity will be discontinued | 1 | 1 | 1
5. Collapse of checker layers | Company employees Contractor employees Supervisors | Visual inspection of combustion chamber wall for the condition Incase of any doubt activity will be discontinued | 1 | 1 | 1
6.Trapping in between objects like rope, fall arrester, electric cable, compress air hoses | Company employees Contractor employees Supervisors | Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 1 | 1
7.Impact due to object, bricks, and hald lamp | Company employees Contractor employees Supervisors | Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 1 | 1
8. Jamming of Ceramic burner air passage. | Company employees Contractor employees Supervisors | Combustion air shut off valve is kept open Thorough inspection of all air passages Oxygen level (min 17 %) is monitored using oxygen monitor Follow WI Safety Awareness/training Use of PPE | 2 | 2 | 4
9. Fall of person from platform, stair case | Company employees Contractor employees Supervisors | Use of certified by Mechanical engineers Safety Awareness /training Use of PPE | 2 | 2 | 4
10. Failure of rope, fall arrester, Alumina ladder, electrical cable. | Company employees Contractor employees Supervisors | Ladder certified by Mechanical engineers Safety Awareness/training Use of PPE | 1 | 1 | 1
11. Failure of channel, platform due to overloading | Company employees Contractor employees Supervisors | Safety Awareness/training Use of PPE Disciplinary action | 1 | 2 | 2
12. Failure of “Confine entry and rescue system”. | Company employees Contractor employees Supervisors | Safety Awareness/training Use of PPE Disciplinary action | 1 | 1 | 1
13. Fall of person inside combustion chamber | Company employees Contractor employees Supervisors | Safety Awareness/training Use of PPE Disciplinary action | 2 | 2 | 4
Physical / Health Hazard
1. Temperature | Company employees Contractor employees Supervisors | Ensure temperature up to 35 degree C before entering Provided proper ventilation Follow work instruction Safety Awareness/training Use of PPE | 2 | 2 | 4
2. Dust | Company employees Contractor employees Supervisors | Controlled comfort ventilation to avoid dust generation Safety Awareness/training Use of PPE */Dust mask | 2 | 2 | 4
3. Back pain due to sudden or heavy load like Ceramic burner blocks. | Company employees Contractor employees Supervisors | Limited restriction of manual handling 2 persons should carry the heavy (60 Kg) load Follow work instruction Safety Awareness/training Use of PPE | 1 | 1 | 1
4.BF gas inhalation | Company employees Contractor employees Supervisors | Continous monitoring by CO monitor Providing ventilation Flare stack should always flare Furnace bleeder should not open during this activity Safety Awareness/traning Use of PPE | 2 | 2 | 4
5. Dust Inhalatin | Company employees Contractor employees Supervisors | Use of Dust mask Safety Awareness/traning Use of PPE | 1 | 1 | 1
6. Suffocation | Company employees Contractor employees Supervisors | Proper ventilisation Oxygen level (min 17 %) is monitored using oxygen monitor Safety Awareness/traning | 1 | 1 | 1
7. Burn Injury from hot surface/ temperature of partition wall | Company employees Contractor employees Supervisors | Distance of one feet is maintained from the hot surface Hot surfaces are covered Cooled down up to 35 degree C Safety Awareness/traning Use of PPE | 2 | 2 | 4
8. Heat | Company employees Contractor employees Supervisors | ORS sachets are provided at the sight. Drinking water is provided at the work site Safety Awareness/traning Use of PPE | 1 | 1 | 1
9. Hot Blast leakage from HBV | Company employees Contractor employees Supervisors | Skilled employee Safety Awareness/traning Use of PPE | 1 | 1 | 1
10. Deficiency of oxygen level | Company employees Contractor employees Supervisors | Proper ventilisation Artificial ventilisation is been created Oxygen level (min 17 %) is monitored using oxygen monitor Safety Awareness/traning Use of PPE. | 1 | 1 | 1
Electrical Hazard
1. Electrical shock from cable | Company employees Contractor employees Supervisors | Only 24 V hand lamps are allowed inside | 1 | 2 | 2
2. Improper lighting | Company employees Contractor employees Supervisors | Providing 24 V hand lamps | 2 | 1 | 2
Behavioural Hazard:
1.Human Behavior-Workmen under influence of alcohol | Company employees Contractor employees Supervisors | Skilled Workmen Safety Awareness/training Use of PPE Disciplinary action | 1 | 2 | 2
2. Human Behavior-Violation of procedure | Company employees Contractor employees Supervisors | Skilled Workmen Inspection/disciplinary action Safety Awareness/training Use of PPE | 2 | 2 | 4
3.Human Behavior-Not wearing PPE’s | Company employees Contractor employees Supervisors | Skilled Workmen Inspection/disciplinary action Safety Awareness/training Use of PPE | 1 | 2 | 2
4.Human Behavior-Not concentrating while working | Company employees Contractor employees Supervisors | Skilled Workmen Safety Awareness/training Use of PPE | 2 | 2 | 4
5. Human Behavior-Fear of confined spaces | Company employees Contractor employees Supervisors | Only authorized persons are allowed inside Safety Awareness/training | 2 | 2 | 4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
Note:
(a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in VL/IMS/VAB/SP41 of System Procedure. | [5 empty] | Signature of the Assessor:-
C) Status(9) Select the drop down for updating status of oppurtunities implementation (Completed /In Progress/ Pending) | [5 empty] | Reviewed Date:- 15.07.2022
d) Revised Likelyhood(10)/Revised Severity of Harm(11)/Risk Level(12) to be updated based on oppurtunity implementation